Broj ugovora: 	2011-01-23-020108

Naziv projekta: Geometar jednakosti

Nositelj projekta: Centar za mirovne studije

Datum: 07.01.2016.

Terms of Reference for Research Assistant for collection and compilation of national and county-level inequality data for Equality Monitoring Framework (EMF) in a sub topic of public policy

- BACKGROUND INFORMATION

Overall objective of the Equality Surveyor project is to contribute to raising capacities of civil society organizations, journalist, and researchers, as well as the public for efficient and effective monitoring of public policies and trends that impact on levels of inequality and discrimination, across eight policy sub-sectors (economics, social welfare, health, education, taxes, political and social participation, the judiciary, and the environment). This project aims to contribute to the overall transparency and openness of the Croatian public administration, as well as to raise awareness and improved understanding of CSOs, researchers and the public at large, in the above mentioned public policy sub-sectors by developing a free, open access and user friendly database that will allow policy makers as well as those whom the policies impact access to key data and trends for decision-making and understanding the impact policies will have on vulnerable groups in Croatia. Through the database, analyses and various activities of the project, the Centre for Peace Studies and its partners intend to not only raise the human capital of CSOs, journalists and activists in terms of being able to understand the repercussions of public policy decisions on social and economic inequality and vulnerable groups, but also to contribute physical capital and resources, through the online database that CSOs, journalists and advocates can use in their research, analyses and advocacy activities related to increased transparency and effectiveness of public policies. We also aim to increase the public awareness and understanding of social and economic inequalities, a topic not yet fully covered or understood in Croatia, in order to increase citizen debate and involvement in the policies which will have an impact on their quality of life.

Specific objective: To collect, compile and analyze public data in eight policy subsectors (economics, social welfare, health, education, taxes, political and social participation, the judiciary, and the environment) as it relates to inequality and vulnerable groups in Croatia, with the objective of increasing transparency of public data, stimulating and informing public debate around various forms of inequalities, their causes and policy prescriptions, and providing a tool (online Equality Monitor) for CSOs, researchers, journalists and activists which they can use to track discrimination and socio-economic inequalities across regions, age groups, gender, socio-economic groups, and other vulnerable groups in Croatia.

- DESCRIPTION OF THE ASSIGNMENT

2.1. Beneficiary of the services

Centre for Peace Studies

2.2. Goals of the service contract

The main goal of the service contract is to secure a research assistant for the manual collection and compilation of public data related to inequality in a policy sub-sector (economics, social welfare, health, education, taxes, political and social participation, the judiciary, and the environment) in order for the Centre for Peace Studies to be able to develop the indicators of inequality for the Equality Surveyor Framework. Because preliminary research has identified that the required data to develop the indicators of inequality are dispersed across various public institutions, and available in various formats (i.e. PDF, Word, online database, excel) the goal of this service contract is to secure a research assistant who is familiar with the various public institutions that collect and provide data, and will be able to collect and compile all of the necessary data (where available) as listed in the list of indicators, in a single and uniform format (excel workbook) which can then be used for the development of the online database, and easy sharing and analysis.

2.3. Specific tasks of the research assistant

- Collect public data (where available) listed in the list of indicators of inequality for the sub topic, as defined by the expert methodology.

- Where data are unavailable from public institutions, undertake internet and desk research to identify if there are other CSOs, think-tanks or researchers who have already collected their own data, and when this is the case include this data

- Compile all of the relevant data in a clean, uniform, and easy to understand excel workbook

- On demand, and if necessary, provide research assistance support for the sub-topic to the Centre for Peace studies should new research or data become available during the collection process

- Final quality check of the data collected to ensure that there are no data errors, as this data will be utilized for developing indicators, analyses and policy prescriptions

2.4. Expected results

- Collection and compilation of sub topic data from list of indicators into a single Excel Workbook, with each of the data required for each indicator in separate excel sheets in a clean and uniform fashion, using standardized terminology and uniform format

- Research support provided to Centre for Peace Studies and partners for the sub topic in question in a timely and professional manner, utilizing standard terminology and present most recent year of data available, from the most trustworthy institution

- Communication with Centre for Peace Studies and partners where additional data deficiencies have been identified through the collection and compilation process

- REQUIRED PROFILE

3.1. Education and professional experience

- University degree in social sciences, economics, or statistics

- Previous experience with collection and compilation of statistics

- Good knowledge of the national statistics bureau of Croatia website and data

- Decent knowledge of English language for accessing Eurostat and Eurostudent website data

- Excellent knowledge of data terminology

- Excellent knowledge of Microsoft Excel

- An interest in the topic of poverty, inequality, and public policies aimed at ameliorating them

3.2. Working language

- Working language is Croatian, but decent knowledge of English is a must

- LOCATION AND DURATION

4.1. Duration

Starting date:  25th January 2016

Ending date: 28th July 2016

4.2. Location

It is expected that the research assistant work from their home, office or school, but that they are available for at least weekly research meetings at the Centre for Peace Studies, and available to schedule more time at the Centre for Peace Studies should it be necessary.

- BUDGET

Each offer will be assessed in terms of the total cost of action, which cannot exceed € 9.500,00 (72.779,50 HRK). The price of offer must be expressed without VAT.

Criteria for selection is based on lowest price.